## Sheet1
Defects
Orange Identified Issue | Slide Id | neXva Response | Steps to fix | Resolved? Yes/No/In Process | Orange Validated? Yes/No | Date Fixed
App installation | 4 | There was no splash screen in the original spec | Splash screen added | Yes |  | 17/04/2014
Home page display | 5 | App icon has been added in center position with Orange background | Fixed | Yes |  | 17/04/2015
App info sheet | 6 | An option has been added to view the entire images once click on banner | Fixed | Yes |  | 17/04/2016
App info sheet | 9 | icon changed and space between icon and text reduced | Fixed | Yes |  | 17/04/2017
App info sheet - Download issue | 10 | Bug fixed for free apps when trying to download.. This was happened only when app wasn't used for some time and (session timed out) . not actually every time.. We identified the issue and fixed it.. | Fixed | Yes |  | 17/04/2018
App info sheet | 11 | FCFA changes GNF | Fixed | Yes |  | 17/04/2019
App info sheet - Rating | 8
App info sheet | 7
Hamburger menu | 12 | bug fixed | Fixed | Yes |  | 18/04/2019
Hamburger menu | 13 | Its CPs decision to determine what should be the category so we are just filtering based on that |  |  |  | 18/04/2019
App stability | 14 |  |  |  |  | 18/04/2019
Log in issue fixed |  |  | Fixed | Yes |  | 19/04/2014
Account log in - forget password | 15 |  | Fixed | Yes |  | 19/04/2014
Account log in | 17 | Translation issue fixed | Fixed | Yes |  | 18/04/2019
About page | 18 |  | Fixed | Yes |  | 18/04/2019
About page (working from home) | 19 | Translations were already added, high res Image yet to be recevied, so dummy image added | Fixed | Yes |  | 19/04/2014
Orange Apps | 20 | bug fixed | Fixed | Yes |  | 18/04/2019
Account page (Reveal wite) |  | Image addition | Fixed | Yes |  | 19/04/2014
Font addtion on the splash screen as suggested Helvetica |  |  | Fixed | Fixed |  | 20/04/2014
Improvements
Home page display | 22 | This was not requested in original design, anyway app name added |  |  |  | 20/04/2014
Account creation | 23
Account creation | 24 | Improvement added with MSISD prefix |  |  |  | 20/04/2014
Buttons | 25
Registration | 26 | Improvement added
Impossible to download | 27 |  |  |  |  | 20/04/2014
Authentication | 28 | Already fixed
18/04/2019
Marcelle's reported issues
Application display is (icons, titles etc) is not steady and changes depending on handset used
Application crashes often and needs to restart after many actions
It is impossible to download any application (connected or not)----application crashes and app is not installed
It is impossible to create a new account or receive OTP
Change password features crashes the app
Content is not relevant and does not match categories nor sub-categories displayed
App installation: .appstore logo to appear after installation .Splashscreen to appear
Homepage display .top carousel image is not ok --- image should be fitted to screen, not shrunk
Application info sheet .Top carousel display is not ok. It does not allow image to be seen and quality of image is poor .stars to note application are not well displayed .scoring display is not ok . Download box is not compliant with design shared .application download fails . (price display for premium apps is wrong: Guinea has GNF not CFA)
Hamburger menu – categories and sub categories display . name display is not always ok and touches + button .applications displayed per category have nothing to do with categories (ex: dual whazaap application in currency/convertors sub category)
Application stability .application crashes after each attempt to download an application .when opening Qelasy application, appstore crashes automatically .change password features crashes application
Account log in: . connexion pop up informs user he is connected when action is not ok . error message is in English
About page: .display is incorrect
Orange Apps: . Top caroussel image and name display are not compliant
Home page display . applications should be displayed with icon AND app name (as for V1 version) . Top paid app section to be hidden until payment is made available
Account creation/log in . insert country prefix automatically in MSISDN field . add information pop up to inform user when his input is wrong